| ## Goal Area – Adult Career Pathways – February 2021 |  |  |  | Working Group Members |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Justification: |  |  |  |  | Maureen, Robin, Sherese, Jon & Hope |  |
| Research indicates that employers are finding it hard to fill “in demand” jobs that require high skills. This employer need could be resolved by “upskilling” workers through the availability of adult career pathways, which will also lead job seekers into living wage jobs. Further, updated visual representations of career paths need to be developed. |  |  |  |  | Plus: |  |
|  |  |  |  |  | *County DelTech Workforce Development Directors |  |
|  |  |  |  |  | *County Technical School – Adult Ed Directors |  |
| Strategy | Action Steps/Key Deliverables List all action steps for each strategy: 1 step/row | Status (See key on 2nd page of form.) |  |  |  |  |
| - Develop common ACP language and graphic models |  | 1a. Adopt WIOA definition for ACP | Completed |  |  |  |
|  |  | 1b. Develop or adopt process graphic that illustrates Delaware’s ACP model. | This has not been started, but it has been discussed |  |  |  |
|  |  | 1c. Review cluster-level graphic representations of ACP models for use by jobseekers and staff (e.g. DE Career Lattices) to develop a Delaware-specific graphic model. | Delaware Career Lattices appear to provide this representation, although there will be a focus on a small # of paths in each county (w/ best outcomes). |  |  |  |
|  |  | 1d. Determine where and how model will be used to engage jobseekers and staff. | Not Started |  |  |  |
| - Environmental Scan/Identify Initial Pathways by County |  | 2a. Break into County Subgroups to identify 1-3 paths/ladders that provide the best intersection of: in-demand jobs with living wages and local training availability. Each subgroup will become familiar with key labor market information for that county. | 1-2020: The County Subgroups met ID best paths/ladders specific to each county. 4/29/20: ACP working group meeting to share county results and plan next steps. Report developed. Completed: Leadership Team approved recommendations |  |  |  |
|  |  | 2b. Use current Delaware Career Pathways logic model (CTE) to analyze data to determine 1). occupational focus of Adult Career Pathways; 2). gaps in occupational training and 3). gaps in populations served by current ACP programming. | 10-20 Began work on gaps analysis to ID additional support needed to improve successful outcomes. Had to put on hold so Training Providers could implement Forward Delaware. |  |  |  |
|  |  | 2b. Vertical alignment to ensure all staff have common understanding – identify staff competencies | Not Started |  |  |  |
| - Conduct best practices research and develop document outlining findings. |  | 3a. Research ACP process graphics used by other states | WINTAC consultants have shared graphics utilized by other state ACP programs. |  |  |  |
|  |  | 3b. Research sample graphic representation of a pathway | Not Started |  |  |  |
|  |  | 3c. Research on-going employer engagement | Not Started |  |  |  |
|  |  | KEY FOR “STATUS” Yellow highlight = STEP COMPLETED gREEN tEXT = oN TARGET rED tEXT = PENDING/GET BACK ON TRACK bLUE TEXT = NOT STARTED/ACTION NOT NEEDED |  |  |  |  |

| Notes |  |  |  |  | Comments |
| --- | --- | --- | --- | --- | --- |
| Date | Strategy #: Specific Action Step |  | Update |
| April Update | 2a. Break into County Subgroups to identify 1-3 paths/ladders that provide the best intersection of: in-demand jobs with living wages and local training availability. Each subgroup will become familiar with key labor market information for that county. |  | County Subgroups have met and identified 1-3 career paths that are in-demand, with local training available and that will lead to living wage careers. We will meet on 4/29 to share information and plan next steps. |
| 4-29-20 ACP Meeting Update | 2a. The 1-2 county-specific path/ladder selections were |  | Will present final recommendations, by county, |
|  | presented to entire working group. County subgroups |  | to WIOA Leadership Team at May or June |
|  | will look at their proposal to see if they want to make |  | Leaders’ meeting. |
|  | changes. ACP Working Group will finalize recommenda- |  |  |
|  | tions and present to WIOA Leadership team for feedback. |  |  |
| 7-2020 | 2a. Recommendations finalized and included in a report. |  | Leadership Team approved the 1-3 recommended paths/county |
| 2-2021 | This group had to put meeting on hold due to COVID-19 and needed effort to set up Forward Delaware training. The plan is to begin meeting again in April. A meeting is in the process of being set up. |  |  |

List of projects/initiatives related to Adult Career Pathways:

- Wilmington Youth Initiative